## Sheet1
material submittal closure rate | IFF Issuance rate | SOC Submission | manpower | discipline | safety incident | rfi closure rate | 2wks ahead acum SPI
0.4 | 0 | 12 | 29.5 | Electrical | 0 | 0.6875 | 0.1
0.4 | 0 | 30 | 30.8333 | Electrical | 0 | 0.70588 | 0.11
0.375 | 0 | 34 | 34 | Electrical | 0 | 0.69231 | 0.15
0.38889 | 0 | 50 | 32.5 | Electrical | 0 | 0.70968 | 0.14
0.52632 | 0 | 40 | 29.1667 | Electrical | 0 | 0.86842 | 0.11
0.47619 | 0 | 30 | 37.8333 | Electrical | 0 | 0.86842 | 0.1
0.43478 | 0.090909 | 15 | 48 | Electrical | 0 | 0.83333 | 0.09
0.42308 | 0.083333 | 21 | 44.1667 | Electrical | 0 | 0.83333 | 0.14
0.35714 | 0.14286 | 26 | 52.8333 | Electrical | 0 | 0.90244 | 0.14
0.44828 | 0.375 | 95 | 64.6667 | Electrical | 0 | 0.85106 | 0.14
0.44828 | 0.38889 | 35 | 70 | Electrical | 0 | 0.75926 | 0.17
0.46667 | 0.30435 | 36 | 82 | Electrical | 0 | 0.74138 | 0.18
0.48 | 0.3 | 36 | 82 | Electrical | 0 | 0.8 | 0.2
0.48 | 0.3 | 36 | 82 | Electrical | 0 | 0.8 | 1
0.44444 | 0.32432 | 96 | 82.8333 | Electrical | 0 | 0.9375 | 1
0.48 | 0.3 | 96 | 85 | Electrical | 0 | 0.9 | 1.11
0.71795 | 0.26829 | 120 | 91.3333 | Electrical | 0 | 0.89041 | 1.12
0.68293 | 0.32558 | 150 | 118.5 | Electrical | 0 | 0.96 | 1.07
0.75 | 0.3 | 120 | 110 | Electrical | 0 | 0.9 | 1.01
0.7561 | 0.3871 | 120 | 115.5 | Electrical | 0 | 0.94805 | 1.05
0.78049 | 0.41429 | 125 | 148 | Electrical | 0 | 0.97403 | 1.05
0.78049 | 0.46479 | 70 | 127.3333 | Electrical | 0 | 0.96203 | 1.05
0.80488 | 0.44595 | 62 | 134.8 | Electrical | 0 | 0.93827 | 1.01
0.78571 | 0.40741 | 68 | 119.8333 | Electrical | 0 | 0.97531 | 1.01
0.78571 | 0.39286 | 72 | 155.6667 | Electrical | 0 | 0.94048 | 1.01
0.83333 | 0.49038 | 82 | 144.6 | Electrical | 0 | 0.97701 | 1.02
0.83333 | 0.59615 | 82 | 185.3333 | Electrical | 0 | 0.95506 | 0.96
0.83721 | 0.67308 | 86 | 197.1667 | Electrical | 0 | 0.97753 | 0.92
0.83721 | 0.67308 | 80 | 201.1667 | Electrical | 0 | 0.97778 | 0.88
0.83721 | 0.64151 | 102 | 220.1667 | Electrical | 0 | 0.95652 | 0.83
0.81818 | 0.64151 | 134 | 272.3333 | Electrical | 0 | 0.95652 | 0.79
0.81818 | 0.71296 | 76 | 215.3333 | Electrical | 0 | 0.97826 | 0.75
0.81818 | 0.6875 | 82 | 245.5 | Electrical | 0 | 0.97826 | 0.7
0.8 | 0.70435 | 138 | 255.5 | Electrical | 0 | 0.96842 | 0.68
0.8 | 0.69231 | 169 | 272.1667 | Electrical | 0 | 0.96842 | 0.69
0.8 | 0.59829 | 82 | 269.3333 | Electrical | 0 | 0.96842 | 0.7
0.73469 | 0.71186 | 100 | 271.6667 | Electrical | 0 | 0.98913 | 0.7
0.7551 | 0.67213 | 34 | 284.3333 | Electrical | 0 | 0.97 | 0.7
0.7551 | 0.61832 | 160 | 290.3333 | Electrical | 0 | 0.92523 | 0.71
0.83673 | 0.79646 | 80 | 335.6667 | Electrical | 0 | 0.96396 | 0.7
0.80392 | 0.72388 | 85 | 348.8333 | Electrical | 0 | 0.95902 | 0.69
0.80392 | 0.69403 | 80 | 340.5 | Electrical | 0 | 0.96721 | 0.69
0.80392 | 0.6791 | 80 | 297.6 | Electrical | 0 | 0.96748 | 0.7
0.80392 | 0.73333 | 80 | 385.6667 | Electrical | 0 | 0.96 | 0.7
0.80392 | 0.73333 | 60 | 418.6667 | Electrical | 0 | 0.96825 | 0.7
0.78431 | 0.73333 | 60 | 425 | Electrical | 1 | 0.93985 | 0.7
0.78431 | 0.78102 | 24 | 404.1667 | Electrical | 0 | 0.93985 | 0.72
0.78431 | 0.81884 | 60 | 515.1667 | Electrical | 0 | 0.94118 | 0.73
0.78846 | 0.81884 | 60 | 687.8333 | Electrical | 0 | 0.94118 | 0.73
0.78846 | 0.80142 | 60 | 635.8333 | Electrical | 0 | 0.94118 | 0.74
0.77358 | 0.80142 | 30 | 739.5 | Electrical | 0 | 0.93431 | 0.76
0.77358 | 0.80142 | 21 | 765.1667 | Electrical | 0 | 0.92754 | 0.77
0.75926 | 0.80142 | 20 | 759.8333 | Electrical | 0 | 0.92086 | 0.79
0.75926 | 0.80142 | 20 | 828 | Electrical | 0 | 0.91429 | 0.79
0.77 | 0.80142 | 25 | 850 | Electrical | 0 | 0.9 | 0.79
0.77 | 0.80142 | 23 | 850 | Electrical | 0 | 0.9 | 0.79
0.77 | 0.80142 | 25 | 850 | Electrical | 0 | 0.9 | 0.79
0.78571 | 0.80142 | 29 | 862.8333 | Electrical | 0 | 0.88235 | 0.79
0.78571 | 0.80142 | 22 | 871.3333 | Electrical | 0 | 0.88235 | 0.8
0.78571 | 0.80142 | 22 | 825 | Electrical | 0 | 0.93464 | 0.8
Note on H15: Tran, Van Hung: before rebaseline SPI
Note on A37: Tan, KhaiX Ee: Breakdown of submittal Document: product catalogue
Note on B37: Tan, KhaiX Ee: breakdown: shop drawing
Note on C37: Tan, KhaiX Ee: 1.0 total SOC based on ratio
Note on D37: Tan, KhaiX Ee: 1.0 b (ii) - take the average
Note on F37: Tan, KhaiX Ee: 1.0
Note on G37: Tan, KhaiX Ee: breakdown

## Sheet2
material receive rate = sum received/sum total
qaqc closure rate = closed/total use weekly
submittal closure rate = sum(returned to date)/sum(submitted to date + returned to date)
safety induction use YTD #
manpower use actual #
SPI use accumulative SPI at the week start